## Actual Schedule 12.16.15
Andrew Hayford, Sebastian Luy		Cache Rules Everything Around Me – Actual Schedule Fall 2015
Updated 11/16/15 - ECE 406		Month/Week Ending
Project Element		2015-09-01					October 2015				November 2015					December 2015
Task Category	Task	09/05/15	09/12/15	09/19/15	09/26/15	10/03/15	10/10/15	10/17/15	10/24/15	10/31/15	11/07/15	11/14/15	11/21/15	11/28/15	12/05/15	12/12/15	12/19/15
Breadboard/Arduino Prototyping							Qualifiers
	Physical Assembly	C – 09/01/15
	LCD driver		C – 09/07/15		I – 09/20/15
	GPS driver	C – 09/04/15					I – 11/04/15
	Haversine implementation	C – 09/06/15					I – 11/15/15
	Time handling	C – 09/01/15					I – 10/26/15	I – 11/01/15
	Tracking mode		C -09/09/15					I -10/26/15
	Button interrupts		C – 09/12/15					I – 11/06/15
	Bluetooth driver			C – 09/14/15					I – 11/11/15			I – 12/05/15
	Waypoints upload						C – 10/31/15					I – 12/05/15
	Waypoints accuracy						C – 10/31/15					I – 12/05/15
	Logging w/ GPS LOCUS				X – 09/26/15
	FRAM driver					C – 09/28/15			I – 10/18/15
	Logging interface					C – 09/28/15
	User interface			C – 9/18/15					I – 10/25/15		I – 11/12/15

Android Application/ Bluetooth							Qualifiers
	Wearable device link			C – 09/18/15					I – 10/29/15		I – 11/12/15
	Web Server link				C – 09/23/15					I -10/29/15					I – 12/10/15
	Error handling				C – 09/23/15					I – 11/12/15				I – 12/10/15
	User interface				C – 09/26/15					I – 10/29/15					I – 12/06/15

Web Server							Qualifiers
	Database management					C – 10/03/15				I – 10/27/15
	Setup and routing		C -09/12/15
	Additional error handling						C – 12/05/15
	User interface					C – 10/03/15				I – 10/26/15		I – 11/12/15
	GPS Plotting		C – 09/09/15					I – 10/25/15		I – 11/12/15

Hardware Component – Qi Charging							Qualifiers
	Qi Receiver Research						C – 10/31/15
	Receiver Design						C – 11/13/15
	Receiver Construction						X – 11/26/15
	MCP73831 PCB Design						C – 11/14/15
	Testing with transmitter						X – 11/26/15
	Prototype assembly						X – 11/26/15
	Additional testing						X – 11/26/15
	Hardware Redesign						C – 11/31/15
	Charger Design						C – 12/06/15
	Charger Testing						C – 12/09/15
	Charger improvements						C – 12/09/15
	Hardware assembly						C – 12/11/15

Final Prototype							Qualifiers
	PCB Seminar						C – 10/08/15
	Arduino assembly						C – 11/06/15
	Arduino testing						C – 11/17/15				C – 12/16/15
	Hardware addition						C – 12/09/15

Department Dates							Qualifiers
	Parts Orders				C – 09/25/15				C – 10/23/15
	PCB Order						C – 10/23/15

Color Code and Key
		Completed before expected date					C	Functionally complete
		Completed after expected date					I	Improvement issued
		Improvements/Supplemental Work					X	Ceased development

## Ideal Schedule 09.11.15
Andrew Hayford, Sebastian Luy		Cache Rules Everything Around Me – Ideal Schedule Fall 2015
09/11/15 - ECE 406		Month/Week Ending
Project Element		September 2015					October 2015				November 2015					December 2015
Task Category	Task	09/05/15	09/12/15	09/19/15	09/26/15	10/03/15	10/10/15	10/17/15	10/24/15	10/31/15	11/07/15	11/14/15	11/21/15	11/28/15	12/05/15	12/12/15	12/19/15
Solderless Breadboard Prototyping							Qualifiers
	Assembly/wiring
	LCD Display
	Accurate speed/distance
	Pushbutton interrupts
	Tracking mode
	Bluetooth communication
	Waypoints feature
	User Interface

Android Application/ Bluetooth							Qualifiers
	Wearable device link
	Web Server link
	User interface

Web Server							Qualifiers
	Database management
	Setup and routing
	Authorization
	User interface
	GPS Plotting

PCB/Perfboard Design							Qualifiers
	PCB Seminar
	Design
	Fabrication/Assembly
	Testing/Redesign

Department Dates							Qualifiers
	Parts/PCB Orders